## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 11-28-2025 | Missing values in email dataset | Sprint 1 | Data Eng. Team | Logical | Removed null records | 11-28-2025 | Closed | Data quality stabilized
2 | QA Team | 2025-07-12 | Label inconsistencies in annotated data | Sprint 1 | Data Team | Standards | Standardized category labels | 2025-08-12 | Closed | Annotation consistency improved
3 | QA Team | 2025-10-12 | Label conflict during validation | Sprint 1 | Data Team | Standards | Re-validated annotated samples | 2025-11-12 | Closed | Final dataset verified
4 | QA Team | 12-15-2025 | Logistic Regression under-fitting | Sprint 2 | ML Team | Logical | Adjusted feature scaling | 12-15-2025 | Closed | Model accuracy increased
5 | QA Team | 12-24-2025 | API response mismatch with frontend | Sprint 2 | Backend Team | Maintainability | Validated inference API outputs | 12-25-2025 | Closed | Backend-Frontend sync resolved
6 | QA Team | 2026-01-01 | Urgency model missed critical emails | Sprint 3 | ML Team | Logical | Added rule-based urgency overrides | 2026-01-01 | Closed | Edge case handling improved
7 | QA Team | 2026-04-01 | Conflict between ML score and rule score | Sprint 3 | ML Team | Logical | Implemented hybrid scoring logic | 2026-05-01 | Closed | Scoring accuracy optimized
8 | QA Team | 2026-09-01 | Poor dashboard data density for email views | Sprint 4 | Frontend Team | User Interface | Redesigned for better UI layout | 2026-10-01 | Closed | UX readability improved
9 | QA Team | 01-16-2026 | Analytics charts failing to load on Safari | Sprint 4 | Frontend Team | User Interface | Updated charting dependencies | 01-18-2026 | Closed | Cross-browser support verified
10 | QA Team | 01-21-2026 | Regression bug in search functionality | Sprint 4 | QA Team | Logical | Applied final patch and re-validated | 01-22-2026 | Closed | System ready for production

## Sheet2
Logical
User Interface
Maintainability
Standards
Others